DELIVERY ROADMAP

# Product Roadmap

A retain–repair–adapt–complete plan for the partially built Ace Club LMS

| Product | Ace Club Learning Management System |
| --- | --- |
| Version | MVP — current agreed scope |
| Date | 30 July 2026 |

Delivery approach: Treat the current portal as an existing product. Audit first, retain working components, repair authentication, adapt the course experience and tracker, then pilot the complete journey.

# 1. Current-state assumptions

## Present or partially built

- Next.js portal and role-oriented interfaces

- Supabase authentication integration

- Magic-link and password-login paths

- Admin and student dashboard components

- Notion-page rendering

- Some form of question or progress tracking

## Known repair or adaptation areas

- Supabase connection and non-working test logins

- Removal of unnecessary Super Admin and production Quick Access behaviour

- Revised curriculum import and fixed instructor mapping

- Cohort schedule and content-release automation

- Simplified spreadsheet-style tracker

- Admin visibility into student-entered tracker data

Planning range: Allow approximately 5–7 engineering weeks plus 1–2 weeks for pilot and stabilisation. Re-estimate after the source code and database audit.

# 2. Delivery phases

## Phase 1 — Recover and audit

Duration: 2–3 working days

- Recover the editable application source, environment configuration and database migrations.

- Map routes, dashboards, authentication, Notion rendering, PDF handling and tracker components.

- Document Supabase tables, roles, policies, triggers and scheduled logic.

- Classify each feature as Keep, Repair, Adapt, Replace or Remove.

Exit gate: Feature inventory, database map, authentication diagnosis and validated estimate.

## Phase 2 — Repair and simplify accounts

Duration: 2–4 working days

- Correct Supabase URL, keys, redirect URLs and deployment configuration.

- Retain only Admin and Student as production roles.

- Create staging Test Admin and Test Student identities.

- Verify magic-link invitations, callbacks, role redirects, logout and deactivation.

- Remove Super Admin and public production Quick Access controls.

Exit gate: New Admin and Student access works; staging test identities pass the full login checklist.

## Phase 3 — Align the master course

Duration: 3–5 working days

- Import the revised fixed curriculum.

- Use curriculum titles and class types.

- Apply DI–Ishan, VA–Tanya and QA–Unnati automatically.

- Associate master Notion pre-reads, PDF worksheets and worksheet question rows.

- Remove placeholder and duplicate course content.

Exit gate: One complete master course contains approved titles, instructors and materials.

## Phase 4 — Cohorts and release automation

Duration: 4–6 working days

- Create cohorts from a start date and agreed schedule.

- Generate class dates and material-release timestamps.

- Make Week 0 available when access is granted.

- Release later pre-reads seven days before class.

- Release PDF worksheets automatically after class.

- Protect locked content from direct URLs.

Exit gate: Two cohorts with different start dates receive correct schedules and releases.

## Phase 5 — Adapt the student experience

Duration: 4–6 working days

- Adapt the dashboard to show the next relevant action.

- Build a chronological timeline with Week 0 and curriculum-derived class cards.

- Place pre-read, class, worksheet and tracker in journey order.

- Show Available now, Upcoming, Available after class and error states.

- Reuse existing Notion and PDF components where viable.

Exit gate: A student can understand what is available now, what is next and what remains locked.

## Phase 6 — Simplify the tracker

Duration: 5–8 working days

- Reuse or migrate the existing progress tables where safe.

- Create student–worksheet–question records.

- Support Done and Come back for review only.

- Add optional time and comment fields.

- Add autosave, saved state and retry behaviour.

- Ensure student-level data isolation.

Exit gate: The spreadsheet-style tracker persists manual student input without data leakage.

## Phase 7 — Adapt admin progress

Duration: 3–5 working days

- Reuse existing admin and student-detail components.

- Show Done, Come back for review, Not updated and last-update totals.

- Allow authorised admins to inspect question-level time and comments.

- Calculate completion only from manual Done entries.

- Remove advanced V2 analytics from the MVP interface.

Exit gate: Admin totals match the student tracker and privacy tests pass.

## Phase 8 — Pilot, launch and stabilise

Duration: 1–2 weeks

- Pilot with one Test Admin, one Test Student and five to ten first-time students.

- Exercise Week 0, a scheduled pre-read, a class and a released worksheet.

- Run authentication, permissions, time-zone, mobile and regression testing.

- Fix critical and high-severity defects.

- Launch the first live cohort and monitor key failures.

Exit gate: End-to-end acceptance passes with no critical defects or cross-student data exposure.

# 3. Recommended implementation sequence

- Repair login, roles and environments before building additional screens.

- Make one complete master course work before importing every curriculum item.

- Make one cohort schedule and release sequence work end to end.

- Complete Week 0, one later pre-read and one worksheet journey.

- Adapt the tracker for one worksheet and expose it to an Admin.

- Generalise the proven vertical slice across the curriculum.

- Pilot with real first-time users before launch.

# 4. Team ownership

| Role | Primary responsibilities |
| --- | --- |
| Product owner | Curriculum, scope, acceptance decisions, pilot approval and launch decision |
| Designer | Dashboard, timeline, material states, tracker and responsive behaviour |
| Front-end engineer | Portal components, Notion rendering, PDF experience, tracker interface and auth screens |
| Back-end engineer | Supabase, roles, policies, scheduling, release automation and tracker persistence |
| QA engineer | Acceptance tests, permissions, time-boundary tests, regression and pilot validation |

Small-team option: One full-stack engineer can combine front-end and back-end ownership, but QA and product acceptance should remain explicit.

# 5. Sprint plan

| Sprint | Goal | Demonstrable outcome |
| --- | --- | --- |
| Sprint 1 | Audit and authentication | Test Admin, Test Student and magic-link journeys work |
| Sprint 2 | Master course and cohorts | A start date generates one correct cohort schedule |
| Sprint 3 | Content journey | Week 0, scheduled pre-read and post-class PDF release work |
| Sprint 4 | Tracker and admin view | Student input persists and Admin sees matching progress |
| Sprint 5 | Pilot and launch | Acceptance, privacy and regression tests pass |

# 6. Account setup runbook

## Production account model

- Production users are Admins and Students.

- Both use email magic links; production passwords are not required.

- The first Admin is created by the technical team, after which the Admin invites students.

- Test Admin and Test Student are staging identities, not additional product roles.

## Information required

- One controlled email address for the first real Admin

- One controlled staging email address for Test Admin

- One controlled staging email address for Test Student

- Supabase project access

- Staging and production portal URLs

- Deployment environment access

## Technical setup steps

- Confirm the application’s Supabase project URL and public key in staging and production.

- Set Supabase Site URL and allowed callback URLs for localhost, staging and production.

- Configure authenticated email delivery and the magic-link email template.

- Create the first Admin authentication user and corresponding application profile.

- Assign the Admin role and verify row-level security permits only authorised admin actions.

- Create Test Admin and Test Student in staging and assign their matching roles.

- Invite a first-time Student through the portal and verify the complete magic-link callback.

- Test expiry, reuse, logout, deactivation and direct access to protected routes.

- Remove or disable Quick Access and all staging identities from the production interface.

## Security rules

- Never place the Supabase service-role key in browser code or public environment variables.

- Never hard-code test passwords into a production bundle.

- Keep test identities and test data in staging.

- Require row-level security for student, cohort and tracker tables.

- Verify a Student cannot retrieve another Student’s tracker data.

# 7. Key dependencies and risks

| Dependency or risk | Mitigation |
| --- | --- |
| Editable source is unavailable | Recover source, migrations and deployment configuration before estimating implementation |
| Supabase fetch failure | Repair environment and network configuration before recreating users |
| Curriculum changes late | Freeze the revised master curriculum before bulk import |
| Notion access changes | Validate page permissions and add observable rendering errors |
| Release-time errors | Store one programme time zone and test exact boundary conditions |
| Tracker data leakage | Use row-level security plus cross-student automated tests |
| Existing tracker does not fit | Migrate only reusable data and replace the interface incrementally |

# 8. Definition of done

- The agreed acceptance criteria pass in staging.

- Automated tests cover authentication, roles, releases and tracker privacy.

- QA verifies mobile and desktop behaviour.

- No critical or high-severity defects remain.

- The feature is demonstrated to the product owner.

- Operational errors are logged and support instructions exist.

- Production configuration contains no staging accounts or Quick Access controls.